## Sheet1
| M | T | W | Th | Fr | Sa | Su
Week 1 |  | Today | Schema v1 DB script v1 | Call | Schema v2 DB script v2 + Dummy data
Week 2 | Req 1 v1 |  |  | Req 1 v2 Req 2 v1 Req 3 v1 Req 4 v1
Week 3 |  | Req 2 v2 Req 3 v2 Req 4 v2 |  | Req 5 v1
Week 4 | Req 5 v2 Req 6 v1 | (Start report - deadlines TBC) |  | Req 5 v2 Req 6 v2 | (Start video - deadlines TBC)
Week 5 |  |  | Submit by 4pm
|  | Name 1 | Name 2
10 | Requirement 1 | Matt | - |  | + every morning catch-up message on Slack: 1. What you did yesterday (esp. any issues) 2. What you're doing today (if anything)
15 | Requirement 2 | Albert | - |  | (or a call)
15 | Requirement 3 | Mehdi | -
15 | Requirement 4 | Dimi | -
15 | Requirement 5 | Matt | -
15 | Requirement 6 | tbc | tbc
15 | Report | Matt | -
| Video | tbc | -
100